## Sheet1
S.No. | Date | Issue | Status | Target Date
1 | 2025-04-11 | Oil name is currently being entered in Recipe. This should be added in the "Material Setting" window like all other material. | Done in our system. To be implemented on site | 2025-05-24
2 | 2025-04-11 | Manual material name when entered in "Bin Settings" page sometimes does not reflect in the "Recipe" page. | Done | Done
3 | 2025-04-11 | For some manual material, when the name is changed in the "Bin Settings" page, it reverts to old value after some time. | Done | Done
4 | 2025-04-11 | Oil weight should not be visible on "Main Page" for Operator (locked condition) | Done in our system. To be implemented on site | 2025-05-24
5 | 2025-04-11 | Pre-weighing-1 gate is opening twice during batch discharge. | Will have to monitor the program while running. Cannot be done remotely. | 2025-05-24
6 | 2025-04-11 | Oil Bin - 4 to be added. Need to check IO provision in PLC
7 | 2025-04-11 | Bagging report not correct |  | 2025-05-26
8 | 2025-04-11 | A recipe number should be present along with recipe name | Done in our system. To be implemented on site | 2025-05-24
9 | 2025-04-11 | Sub-totals for WH, Manual and Oil should be shown on "Recipe Page". This should be visible on Recipe Page for Operator also in locked view. | Done in our system. To be implemented on site | 2025-05-24
10 | 2025-04-11 | In report, total weight should be shown below each material. |  | 2025-05-28
11 | 2025-04-11 | Replace/Delete button should not be present on Repice page in locked view | Done | Done
12 | 2025-04-11 | Bin Settings and Manual settings should not be visible in locked view. | Done | Done
13 | 2025-04-11 | Pre-weigh should discharge after some time delay to avoid jamming in conveyor. |  | 2025-05-24
14 | 2025-04-11 | Bin sequence logic to be added in recipe. |  | 2025-05-28
15 | 2025-04-11 | To avoid data loss in reports, alarm pop up should be generated in case data is not stored due to any reason. | Done in our system. To be implemented on site | 2025-05-24
16 | 2025-05-22 | Manual material weight is sometimes showing less than set weight ( 2-4kg against set weight of 40kg). Is this an issue with reporting or with the process.
17 | 2025-05-22 | Recipe getting deleted automatically from the Recipe page.