## production Receipt (hidden)
Production Recepit (DPR)
S. No. | Date | ERP Issue | Remarks Fron CNC Team | Status | Issue Resolved On | Remarks
1 | 2021-02-12 | UOM not as per requirement | Need option or drop down for NOS & Set | Pending from Sales
2 | 2021-02-12 | Remarks Option Required | Option required for remarks | Completed | 2021-02-20 | NCCMS
3 | 2021-02-12 | Brand Name Required | Brank Name required for eg. Lark Make to ensure In-house production | Completed | 2021-02-12 | Parteek Sir
4 | 2021-02-12 | Print Option Required | option required | Completed | 2021-02-20 | NCCMS
5 | 2021-02-12 | Option required for material receiving with remarks |  | Pending |  | NCCMS
6 | 2021-02-12 | Same item code for hammers | Same item code required for hammer of QGA & FSHM hammer Mill (For eg. QGA 20-40/FSHM 20-40) | Pending from Sales
7 | 2021-02-13 | Item Codes are not reflecting | Some of the item code are not reflecting when we will search from their item name (For Eg. FSHM-1015 Full Screen Hammer Mill 7.12 mm) | Completed | 2021-02-20 | NCCMS
8 | 2021-03-06 | Option required for material handover against particular work order |  | Pending |  | NCCMS
9 | 2021-03-09 | Some Item codes are not reflecting while search (Foreg - MCFIMS2241) |  | Pending from Sales |  | NCCMS + Sales@Mr. Parteek
10 | 2021-06-29 | up & Down Scrolling option not working in Productin DPR while searching particular items |  |  |  | NCCMS
11 | 2021-07-07 | Procedure for pellet die handover in dispatch Dpt. against W.O and inventory
12 | 2021-07-07 | Duplicate Items not added in same DPR sheet | option required to add duplicate item in sheet |  |  | NCCMS

## Sheet1 (hidden)
Planning + Production
S. No. | Date | ERP Issue | Remarks Fron CNC Team | Status | Issue Resolved On | Remarks
1

## Program Master (hidden)
Production Recepit (DPR)
S. No. | Date | ERP Issue | Remarks Fron CNC Team | Status | Issue Resolved On | Remarks
1 | 2021-08-02 | For Pad Width column there was only provision of making numeric entery upto 3 digits | For same entery upto 10 digit was required (Foreg, 56.5+56.5) | Pending By NCCMS | 2021-08-03 | Done
2 | 2021-08-02 | Serial No. are not in sequence | Serial No. are not in sequence | Pending By NCCMS | 2021-08-03 | Done
3 | 2021-08-02 | Program revision No. & Drawing revision No. column should be onsidered as mandatory | Option required for to eliminate non availability of complete drawing no. with its revision no. | Pending By NCCMS | 2021-08-03 | Done
4 | 2021-08-02 | Rev.No Name should be amended | Names should be changed by drawing Rev no. & Program Rev. No. | Pending By NCCMS | 2021-08-03 | Done

## JCN
Production Recepit (JCN)
S. No. | Date | Module | ERP Issue | Remarks From CNC Team | Remarks from NCCMS | Status | Issue Resolved On | Remarks
1 | 2021-08-13 | JCN Templates | First Row of JCN templates should be freezed | required to ease entery of data | Done |  |  | From NCCMS
2 | 2021-08-13 | JCN Templates | Purpose of slections of teams or helpers in JCN Templates | As it was was not possible to confirm the team or operator at the time of JCN entery | Discuss later |  |  | From NCCMS
3 | 2021-08-13 | JCN Templates | Cost per hour in Job preparation template was required upto to 6 decimal |  | Done |  |  | From NCCMS
4 | 2021-08-13 | JCN Templates | In inspection template , there is no such record of person inpecting the job | Name of Quality Assis tance is required | Done |  |  | From NCCMS
5 | 2021-08-13 | Work Station calender | Option required for Selecting particular machine in work station calender |  | Discuss later |  |  | From NCCMS
6 | 2021-08-13 | JCN | Kindly specify the purpose of selection of Engineer / Supervisor in JCN |  | Discuss later |  |  | From NCCMS
7 | 2021-08-13 | JCN | Drawing no. should be automatically filled from the selected work order |  | Done |  |  | From NCCMS
8 | 2021-08-13 | JCN | Drawing file No. should be amended by Drawing No. |  | Done |  |  | From NCCMS
9 | 2021-08-13 | JCN | Technical S[pecification were not as per the requirement shared by the cnc team | Refer to Manpreet Sir for the requirement | Done |  |  | From NCCMS
10 | 2021-08-13 | JCN | Special comment mentioned in the work order required while JCN entery |  | Done |  |  | From NCCMS
11 | 2021-08-13 | JCN | Attachment in the work order should be linked with JCN |  | Done |  |  | From NCCMS
12 | 2021-08-13 | JCN | Planned hours should be amended by planned days + Similar with Actual hour taken should be amended by Actual days taken |  | Discuss later |  |  | From NCCMS
13 | 2021-08-13 | JCN | Document upload option not working |  | Done |  |  | From NCCMS
14 | 2021-08-13 | JCN | How priority option will work , as JCN of all department are reflecting in same |  | Done |  |  | From NCCMS
15 | 2021-08-13 | JCN | Also let us know where we have to update die status either in work orderlist or in JCN |  | Discuss later |  |  | From NCCMS
16 | 2021-08-13 | JCN | Reference of JCN planned date and end date |  | Discuss later |  |  | From NCCMS
1 | 2021-10-08 | JCN Status Summary | In case work order is having multiple item, how we will confirm that the JCN for item No. 1 was completed or not |  | Done | Done | 2021-10-14
2 | 2021-10-08 | JCN Status Summary | While planing jon on any work station , work station available on column was not working . |  | Done | Done | 2021-10-14
3 | 2021-10-08 | JCN Status Summary | While planning job on one work station, system will generate 100% contribution require alarm. |  | Under Discussion | Pending
4 | 2021-10-08 | JCN Status Summary | Previous load available on the machine was not visible |  | Done | Working From CNC required | 2021-10-14
5 | 2021-10-08 | Job Movement Slip | while selecting JON , item name in case of roll shell's work order, was not shown |  | Done | Working From CNC required | 2021-10-14
6 | 2021-10-08 | Job Movement Slip | After selecting the JON no. and ther required details, item description option was not working |  | Done | Working From CNC required | 2021-10-14 | Further working on the mentioned Module was pending due to the mentioned reason
7 | 2021-10-08 | Option required to create work order or job order | Option required to work on inter department job work scheduling |  | Done | Working From CNC required | 2021-10-14 | Discussed with Mr. Manpreet
8 | 2021-10-08 | How to make work order for inventory of dies | Option required fr inventory precurement |  | Done | Working From CNC required | 2021-10-14 | Discussed with Mr. Manpreet
9 | 2021-11-10 | JCN | Current Job details required while planning jobs in work stations
10 | 2021-11-10 | JCN | Work order description master details required
11 | 2021-11-10 | JCN | option required for planning multile operations on single work station
12 | 2021-11-10 | JCN | Die Category option not working in work orderes
13 | 2021-11-10 | JCN | While making single JCN of work order having muliple items, second job will automatically planned on the same work station
14 | 2021-11-10 | JCN | Load calculation option not working in JCN
15 | 2021-11-10 | JCN | Job Quantity not reflecting on work station
16 | 2021-11-10 | JCN | While updating die status in W.O die status report, work order pop up option not working
1 | 2023-02-01 | PPC Job Summary | While making any JCN we have to mannually enter start date for the first work station only after that system will calculate the next particular timing | system will auto calculate the date & time of availability | Pending | Pending
2 | 2023-02-01 | JCN Templates | Drawing Availability + R.M Availability + Machining Part + Purchase Items | Availability should be autofilled in the system , as once we ensure the availability there is no need to recheck or reconfirm the data | Pending | Pending
3 | 2023-02-01 | JCN Templates | Job Prepartation +Packing Info + Dispatch status - Mentioned template was not in our scope,same will not allow us to close the JCN | Kindly remove or close | Pending | Pending
4 | 2023-02-01 | JCN Templates | Final Inspection | Kindly define our working in the this system , without this JCN closing was not feasible | Pending | Pending
5 | 2023-02-01 | Sales Report - Work order die status | even after updating the blank no. and status of work order some of the blanks are not shown in the mentioned report. For eg. Blank No. 9509 against work order no. 9037 | Kindly conclude for the issue so that we can shift our stock of dies sheet working in ERP system | Pending | Pending